## WBS Schedule
WBS Code | Task / Subtask | Description | Assigned Dev | Duration (days) | Predecessor(s) | Start Date (Planned) | Deadline (Planned) | Date Started (Actual) | Date Finished (Actual) | Status | Notes / Deliverable
0.0 | Project Planning & Design | Define project scope, MVP features, team roles, and delivery plan | All Members | 5 | - | 2026-08-17 | 2026-08-21 |  |  | Review actual progress
0.1 | Requirements Gathering | Confirm customer, employee, and owner needs; confirm order workflow | Rodel Tan | 3 | - | 2026-08-17 | 2026-08-19 |  |  | Review actual progress
0.2 | System Requirements | Finalize functional requirements, non-functional requirements, and acceptance criteria | Rodel Tan | 3 | 0.1 | 2026-08-19 | 2026-08-21 |  |  | Review actual progress
0.3 | Database Design | Design ERD and fields for users, customers, orders, services, payments, audit logs | Ian Ashtune Navarro | 4 | 0.1 | 2026-08-20 | 2026-08-24 |  |  | Review actual progress
0.4 | UI/UX Wireframes | Create core page wireframes for customer, employee, and owner | Philip Mendoza II | 4 | 0.1 | 2026-08-20 | 2026-08-24 |  |  | Review actual progress
0.5 | Architecture & Task Setup | Confirm application structure, repository, coding conventions, and task board | Ian Ashtune Navarro | 2 | 0.2 | 2026-08-22 | 2026-08-24 |  |  | Review actual progress
1.0 | Application Foundation | Set up project, database connection, shared layout, and base navigation | Ian Ashtune Navarro + Philip Mendoza II | 7 | 0.3, 0.5 | 2026-08-25 | 2026-09-01 |  |  | Review actual progress
1.1 | Project Setup | Create project folders, repository, environment configuration, and starter pages | Ian Ashtune Navarro | 3 | 0.5 | 2026-08-25 | 2026-08-27 |  |  | Review actual progress
1.2 | Database Setup | Create database and initial tables; verify database connection | Ian Ashtune Navarro | 4 | 0.3, 1.1 | 2026-08-28 | 2026-09-01 |  |  | Review actual progress
1.3 | Shared Layout | Build responsive navigation, header, footer, and reusable UI styles | Philip Mendoza II | 4 | 0.4, 1.1 | 2026-08-28 | 2026-09-01 |  |  | Review actual progress
2.0 | Authentication & Role Access | Implement login, logout, session handling, and role-based access | Ian Ashtune Navarro | 7 | 1.2 | 2026-09-02 | 2026-09-09 |  |  | Review actual progress
2.1 | Login Form | Create login interface and input validation | Philip Mendoza II | 3 | 1.3 | 2026-09-02 | 2026-09-04 |  |  | Review actual progress
2.2 | Authentication Logic | Verify credentials, hash passwords, and create secure login session | Ian Ashtune Navarro | 4 | 1.2, 2.1 | 2026-09-05 | 2026-09-09 |  |  | Review actual progress
2.3 | Role-Based Routing | Direct users to customer, employee, or owner dashboard and enforce permissions | Ian Ashtune Navarro | 3 | 2.2 | 2026-09-07 | 2026-09-09 |  |  | Review actual progress
3.0 | Customer & Service Management | Create customer records and configurable laundry service/pricing records | Rhealyn Cabarloc | 7 | 1.2, 2.3 | 2026-09-10 | 2026-09-17 |  |  | Review actual progress
3.1 | Customer Records | Add, view, search, and edit customer details | Rhealyn Cabarloc | 4 | 2.3 | 2026-09-10 | 2026-09-14 |  |  | Review actual progress
3.2 | Laundry Services | Add and manage service types and price rates | Rhealyn Cabarloc | 4 | 1.2 | 2026-09-12 | 2026-09-16 |  |  | Review actual progress
3.3 | Form Validation | Validate required customer and service fields | Rhealyn Cabarloc + Rodel Tan | 2 | 3.1, 3.2 | 2026-09-16 | 2026-09-17 |  |  | Review actual progress
4.0 | Laundry Order Management | Create orders, calculate price, record weight, and update processing status | Ian Ashtune Navarro + Rhealyn Cabarloc | 12 | 3.1, 3.2 | 2026-09-18 | 2026-09-30 |  |  | Review actual progress
4.1 | Create Laundry Order | Record customer, order number, service, weight, date, and estimated ready time | Rhealyn Cabarloc | 5 | 3.1, 3.2 | 2026-09-18 | 2026-09-23 |  |  | Review actual progress
4.2 | Price Calculation | Calculate total price using service rate and weight or configured pricing rule | Ian Ashtune Navarro | 4 | 4.1 | 2026-09-23 | 2026-09-26 |  |  | Review actual progress
4.3 | Order Status Workflow | Implement Received, Queued, Processing, Ready for Pickup, and Claimed | Ian Ashtune Navarro + Rhealyn Cabarloc | 5 | 4.1 | 2026-09-25 | 2026-09-30 |  |  | Review actual progress
4.4 | Order Search & Details | Search orders by order number/customer and view order details | Rhealyn Cabarloc | 4 | 4.1 | 2026-09-27 | 2026-09-30 |  |  | Review actual progress
5.0 | Role Dashboards & Tracking | Build employee work queue, customer order tracking, and owner overview | Philip Mendoza II + Rhealyn Cabarloc | 9 | 4.3 | 2026-10-01 | 2026-10-10 |  |  | Review actual progress
5.1 | Employee Dashboard | Show active orders and controls for updating order status | Philip Mendoza II | 4 | 4.3 | 2026-10-01 | 2026-10-04 |  |  | Review actual progress
5.2 | Customer Order Tracking | Show order number, current status, and estimated ready time | Rhealyn Cabarloc + Philip Mendoza II | 4 | 4.3 | 2026-10-04 | 2026-10-07 |  |  | Review actual progress
5.3 | Owner Dashboard | Show total orders, active orders, ready/unclaimed orders, and basic summaries | Philip Mendoza II | 4 | 4.3 | 2026-10-06 | 2026-10-09 |  |  | Review actual progress
5.4 | Workload Indicator | Display Low, Moderate, Busy, or Very Busy based on active workload rules | Ian Ashtune Navarro + Philip Mendoza II | 2 | 5.3 | 2026-10-09 | 2026-10-10 |  |  | Review actual progress
6.0 | Payments & Transaction Transparency | Record payments and maintain reviewable order change history | Ian Ashtune Navarro + Rhealyn Cabarloc | 9 | 4.2, 4.3 | 2026-10-11 | 2026-10-20 |  |  | Review actual progress
6.1 | Payment Recording | Record amount, payment method, and unpaid/partial/paid status | Rhealyn Cabarloc | 4 | 4.2 | 2026-10-11 | 2026-10-14 |  |  | Review actual progress
6.2 | Audit Log | Record old/new values, changed field, user, timestamp, and reason where applicable | Ian Ashtune Navarro | 5 | 4.3 | 2026-10-14 | 2026-10-18 |  |  | Review actual progress
6.3 | Owner Change Review | Allow owner to review weight, price, service, and status changes | Philip Mendoza II | 3 | 6.2 | 2026-10-18 | 2026-10-20 |  |  | Review actual progress
6.4 | Discrepancy Flag | Flag changed weight or price for owner review without automatically alleging misconduct | Ian Ashtune Navarro + Rhealyn Cabarloc | 2 | 6.2 | 2026-10-19 | 2026-10-20 |  |  | Review actual progress
7.0 | Integration & Testing | Integrate modules, test user journeys, fix priority bugs, and validate access controls | All Members | 8 | 5.0, 6.0 | 2026-10-21 | 2026-10-29 |  |  | Not Started
7.1 | Authentication Testing | Test login/logout and permissions for all three roles | Rodel Tan + Ian Ashtune Navarro | 2 | 2.3 | 2026-10-21 | 2026-10-22 |  |  | Not Started
7.2 | Functional Testing | Test customer records, orders, price calculation, status, payments, and audit trail | Rodel Tan + Rhealyn Cabarloc | 4 | 5.0, 6.0 | 2026-10-22 | 2026-10-26 |  |  | Not Started
7.3 | Responsive UI Testing | Test common pages on desktop and mobile-sized screens | Philip Mendoza II + Rodel Tan | 2 | 5.0 | 2026-10-24 | 2026-10-25 |  |  | Not Started
7.4 | Bug Fixing & Retesting | Fix critical bugs and rerun failed test cases | All Members | 4 | 7.1, 7.2, 7.3 | 2026-10-26 | 2026-10-29 |  |  | Not Started
8.0 | Finalization & Documentation | Complete remaining features, prepare user guide, final report, demo data, and presentation | All Members | 28 | 7.4 | 2026-10-30 | 2026-11-29 |  |  | Not Started
8.1 | Feature Completion & Refinement | Finish any remaining MVP work and refine core workflows based on testing | All Members | 10 | 7.4 | 2026-10-30 | 2026-11-08 |  |  | Not Started
8.2 | Security & Data Validation Review | Review access control, validation, error handling, and customer-data protection | Ian Ashtune Navarro + Rodel Tan | 5 | 8.1 | 2026-11-09 | 2026-11-13 |  |  | Not Started
8.3 | User Guide & Final Report | Prepare instructions for customer, employee, and owner; finalize report and screenshots | Rodel Tan | 7 | 8.1 | 2026-11-09 | 2026-11-16 |  |  | Not Started
8.4 | User Acceptance Testing | Ask the laundry shop client to try the agreed workflows and provide feedback | All Members | 5 | 8.2, 8.3 | 2026-11-17 | 2026-11-21 |  |  | Not Started
8.5 | Final Bug Fixes & Demo Rehearsal | Fix priority issues, prepare demo accounts/data, and rehearse presentation | All Members | 5 | 8.4 | 2026-11-22 | 2026-11-26 |  |  | Not Started
8.6 | Final Submission | Final verification, backup, presentation, and submission | All Members | 3 | 8.5 | 2026-11-27 | 2026-11-29 |  |  | Not Started

## Team Roles
Developer ID | Member Name | Suggested Role | Main Responsibilities
Dev 1 | Ian Ashtune Navarro | Backend / Database Lead | Project setup, database, authentication, order logic, audit logging, integration
Dev 2 | Rhealyn Cabarloc | Core Features Developer | Customer/service records, order forms, pricing, order workflow, payments
Dev 3 | Philip Mendoza II | UI / Frontend Developer | Wireframes, shared layout, dashboards, customer tracking, responsive UI
Dev 4 | Rodel Tan | Requirements / QA / Documentation | Requirements, test cases, documentation, screenshots, user guide, presentation, and QA support

## Milestones
Target Date | Milestone
2026-08-17 | Project start; begin requirements and planning
2026-08-24 | Initial requirements, database design and wireframes target
2026-09-09 | Application foundation and role-based login target
2026-09-17 | Customer and service management target
2026-09-30 | Core laundry order workflow target
2026-10-10 | Customer, employee, and owner dashboards target
2026-10-20 | Payments and transaction transparency target
2026-10-29 | Integration testing and priority bug fixes target
2026-11-21 | Client/user acceptance testing target
2026-11-29 | Final demo and submission target